## Milestones
Milestone Mo. | Major Task | Description | Hours Estimation | Starting Date | Ending Date | Electron's Remarks | Cole's Remarks
1 | Part Searching and Analysis | Searching parts/components/modules and also comparing cost. | 45 Hours | 29th March 2021 | 6th April 2021 | Main procruement will be done from LCSC as per Sir Cole remakrs. But for prototype testing, I will prefer Digikey, Mouser, Arrow, RS etc.
2 | Library Creation and Parts Selection continued | Schematic Symbol and PCB Foot print will be designed and also part selection will be continued (For Example: Resistor, Capacitor and other IC) | 20 Hours | 7th April 2021 | 11th April 2021 | AD 20, CAD Software will be used. Most of the parts will be pick up from Digikey but Mr. Cole already told me that main sourcing will be done from LCSC. But for refrence, I still use Mouser and Digikey.
3 | Schematic/Circuit Designing | Circuit Designing and testing will be done (if possible) | 40 - 50 Hours | 12th April 2021 | 20th April 2021 | Datasheet reference will be take for proper design.
4 | PCB Parts Placement | Parts placement will be done. | 8-12 Hours | 21st April 2021 | 22nd April 2021 | This is very critical point, I am gonna need Mechanical designer assistance to check proper component placement and height
5 | PCB Layout Desiging | Routing will be done. | 50 Hours | 23rd April 2021 | 30th April 2021 | Once the Schematic Design is lock and parts placement is done, this task will be very but time consuming
6 | PCB Core files creation | Core Files, will be created and dealing with manufacturers | 2 Hours | 30th April 2021 |  | Step Files will be generated also for placement purpose
7 | Manufacturing Process (Prototype - 5 Samples) | PCB fabrication and Assembly Parts/Component Procurement. | 2 Weeks Should be considered |  |  | Have warehouse in China and also partnered with multiple companies. It will take approx 1 Week for parts procurement and 2 weeks for assembly. The Shipping will take 5-7 Days.
8 | Tesitng and Programming Phase | PCB Boards will be tested. Noise testing, Connector positon and harnessing will be tested. | TBD |  |  | Test program will also be requried to check controller connection with Stepper Driver and with various sensors. Need more assistance from Sir Cole, I am not aware with proper software strategy here but I will make sample code for my hardware testing
9 | Error Correction and modifcation | Changes in Schematic Design, parts addition / PCB Design Changes |  |  |  | This milestone is TBD, wether the first prototype will run successfully or we gonna need another revision.
10 | Manufacturing Process (Prototype - 5 Samples) | TBD | TBD |  |  | TBD
11 | Tesitng and Programming Phase | TBD | TBD |  |  | TBD
12 | ----- | ----- | ----- | ----- | ----- | ----- | -----
13 | ----- | ----- | ----- | ----- | ----- | ----- | -----
Above hours are estimated but dates are confirmed from my end. I will try to complete both PCB in this one month specturum, and send it for production (Prototype Phase - 1). There are some typo mistake, please neglect it.